## Daily Activation_Template
PIC | Copy | Copy | Copy | Copy | Copy | Copy | Copy | Copy |  |  |  | Copy | Copy | Copy | Copy | Copy | Copy | Dika Team | Nana | Agung | Agung | Nana | Nana | Nana | Nana | Nana | Nana | Nana | Nana | Nana | Nana | Formula | Agung/Alfian | All
Source | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily |  |  |  | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily | Pivot Daily
Input
212 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 |  |  |  | 67 | 67 | 67 | 67 | 67 | 67 | 0 | 0 | 67 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Activation - Plan Date | Branch Name | Branch Manager Name & Phone | Site Code | Site Name | Site City | SDWAN - Host Name | IP Astinet (CE) | IP Astinet (PE) | IP LAN | IP LAN | Main Link - IP LAN | SDWAN - Order Number | SDWAN - SID Number | SDWAN - Order Assignment | SDWAN - Order Task Status | FE 3rd Party | SDWAN - Order Task Progress | FE Name_Phone Number | PIC DS | IP LAN NEW | Target Start Time | Activation Status | FE Arrival Time | EDP Arrival Time | Pretest Start Time | P2P Start Time | Migration Start Time | Postest Start Time | Failover Test Start Time | Activation Completion Time | Duration (Hours) | Issue (Need Support) | Remarks | PIC INTERNAL | PIC External
1 | 2026-09-09 | BALI | YOHANES MICHAEL | T9NA | IMAM BONJOL | Kabupaten Buleleng | 0208-D3-SGR-IDM-T9NA-BALI | 36.67.43.157 | 36.67.43.156 | 10.55.150.192/27 | 1-71801328543 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Jamal |  |  | hilmi | Alfian | [13 empty] | ALFIAN | aqis
2 | 2026-09-09 | BALI | YOHANES MICHAEL | TIQI | YEH GANGGA | Kabupaten Tabanan | 0208-D3-TBN-IDM-TIQI-BALI | 36.67.150.43 | 36.67.150.42 | 10.55.23.128/27 | 1-71801517771 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Jamal |  |  | mando | Alfian | [13 empty] | ALFIAN | aqis
3 | 2026-09-09 | BALI | YOHANES MICHAEL | TPAT | NGURAH RAI 42 | Kabupaten Buleleng | 0208-D3-SGR-IDM-TPAT-BALI | 36.91.119.55 | 36.91.119.54 | 10.55.11.192/27 | 1-71801662385 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Jamal |  |  | pasha | Alfian | [13 empty] | ALFIAN | aqis
4 | 2026-09-09 | BALI | YOHANES MICHAEL | TTXT | GUNUNG AGUNG | Kabupaten Tabanan | 0208-D3-TBN-IDM-TTXT-BALI | 36.67.45.47 | 36.67.45.46 | 10.55.142.32/27 | 1-71801102622 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Jamal |  |  | raihaan | Alfian | [13 empty] | ALFIAN | aqis
5 | 2026-09-09 | BANJARMASIN | SUSIANTO | T50M | MISTAR COKROKUSUMO 4 | Kota Banjarbaru | 0208-D4-BBR-IDM-T50M-BANJARMASIN | 36.67.112.65 | 36.67.112.64 | 10.63.8.160/27 | 1-71801989027 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Febri Aditya |  |  | daris | Alfian | [13 empty] | ALFIAN | aqis
6 | 2026-09-09 | BANJARMASIN | SUSIANTO | TH2W | TRIKORA ANEKA TAMBANG | Kota Banjarbaru | 0208-D4-LUL-IDM-TH2W-BANJARMASIN | 36.67.113.247 | 36.67.113.246 | 10.63.36.224/27 | 1-71823099103 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Febri Aditya |  |  | rayyan | Alfian | [13 empty] | ALFIAN | aqis
7 | 2026-09-09 | BANJARMASIN | SUSIANTO | TMYX | A. YANI KM 37.5 | Kabupaten Banjar | 0208-D4-LUL-IDM-TMYX-BANJARMASIN | 36.67.112.85 | 36.67.112.84 | 10.63.9.64/27 | 1-71807246142 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | ITSC | Pre Config SD-WAN | Haris Yulianto |  |  | ivansyah | Alfian | [13 empty] | ALFIAN | aqis
8 | 2026-09-09 | BEKASI | TATANG | T4CD | KASUARI | Kabupaten Bekasi | 0208-D2-JBB-IDM-T4CD-BEKASI | 36.91.54.79 | 36.91.54.78 | 10.44.38.1/27 | 1-71857222606 | 0 | 1600120 ¦ Sahril Dian Hasapi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | idrus | Alfian | [13 empty] | ALFIAN | aqis
9 | 2026-09-09 | BEKASI | TATANG | T7LL | CAHAYA KEMANG 2 | Kota Bekasi | 0208-D2-DNI-IDM-T7LL-BEKASI | 36.66.123.155 | 36.66.123.154 | 10.44.6.161/27 | 1-71854238344 | 0 | 855457 ¦ Dwi Syifa | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | haidar | Alfian | [13 empty] | ALFIAN | aqis
10 | 2026-09-09 | BEKASI | TATANG | F1DI | GRAHA CIKARANG | Kabupaten Bekasi | 0208-D2-JBB-IDM-F1DI-BEKASI | 36.95.107.9 | 36.95.107.8 | 10.44.13.128/27 | 1-71823031102 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ferdi | Alfian | [13 empty] | ALFIAN | aqis
11 | 2026-09-09 | BOGOR 2 | SUNADI | TZGU | SYNTHESIS HUIS RESIDENCE | Kota Administrasi Jakarta Timur | 0208-D2-PSR-IDM-TZGU-BOGOR2 | 36.93.175.223 | 36.93.175.222 | 10.65.52.161/27 | 1-71804684821 | 0 | 1600120 ¦ Sahril Dian Hasapi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Kevin | Alfian | [13 empty] | ALFIAN | aqis
12 | 2026-09-09 | BOGOR 2 | SUNADI | TMY3 | KALISARI PEKAYON NO. 107 | Kota Administrasi Jakarta Timur | 0208-D2-GAN-IDM-TMY3-BOGOR2 | 36.95.107.85 | 36.95.107.84 | 10.65.23.129/27 | 1-71804685535 | 0 | 0 | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Adnan | Alfian | [13 empty] | ALFIAN | aqis
13 | 2026-09-09 | JAKARTA 1 | DANI HIDAYAT | T6ON | SPBU PLUIT PERMAI | Kota Administrasi Jakarta Utara | 0208-D2-MKR-IDM-T6ON-JAKARTA1 | 36.89.118.171 | 36.89.118.170 | 10.39.13.160/27 | 1-71825949156 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | hilmi | Alfian | [13 empty] | ALFIAN | aqis
14 | 2026-09-09 | JAKARTA 1 | DANI HIDAYAT | T8RY | HARCO MANGGA BESAR | Kota Administrasi Jakarta Pusat | 0208-D2-KTZ-IDM-T8RY-JAKARTA1 | 36.92.205.145 | 36.92.205.144 | 10.39.186.96/27 | 1-71827918602 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | mando | Alfian | [13 empty] | ALFIAN | aqis
15 | 2026-09-09 | JAKARTA 1 | DANI HIDAYAT | TSUI | TEBET TIMUR DALAM | Kota Administrasi Jakarta Selatan | 0208-D2-TBE-IDM-TSUI-JAKARTA1 | 36.91.186.39 | 36.91.186.38 | 10.39.68.224/27 | 1-71832186591 | 0 | 1600120 ¦ Sahril Dian Hasapi | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | pasha | Alfian | [13 empty] | ALFIAN | aqis
16 | 2026-09-09 | JAKARTA 1 | DANI HIDAYAT | TUHG | APARTEMEN PESONA BAHARI | Kota Administrasi Jakarta Pusat | 0208-D2-KTZ-IDM-TUHG-JAKARTA1 | 36.92.143.49 | 36.92.143.48 | 10.39.20.192/27 | 1-73092586490 | 0 | 20015074 ¦ Alfian Hafidzh | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | raihaan | Alfian | [13 empty] | ALFIAN | aqis
17 | 2026-09-09 | JAKARTA 2 | DANI HIDAYAT | TKCG | PONDOK KELAPA 1 | Kota Administrasi Jakarta Timur | 0208-D2-PDK-IDM-TKCG-JAKARTA2 | 36.89.120.85 | 36.89.120.84 | 10.66.148.160/27 | 1-71791420706 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | daris | Alfian | [13 empty] | ALFIAN | aqis
18 | 2026-09-09 | JAKARTA 2 | DANI HIDAYAT | TL4P | DANAU SUNTER UTARA B6 | Kota Administrasi Jakarta Utara | 0208-D2-STR-IDM-TL4P-JAKARTA2 | 36.89.118.89 | 36.89.118.88 | 10.66.158.32/27 | 1-71787329782 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | rayyan | Alfian | [13 empty] | ALFIAN | aqis
19 | 2026-09-09 | JAKARTA 2 | DANI HIDAYAT | TX6G | FRESH CIPINANG BALI NO 8 | Kota Administrasi Jakarta Timur | 0208-D2-JTN-IDM-TX6G-JAKARTA2 | 36.95.107.93 | 36.95.107.92 | 10.66.146.161/27 | 1-71805706805 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ivansyah | Alfian | [13 empty] | REDHO | aqis
20 | 2026-09-09 | JAKARTA 2 | DANI HIDAYAT | FTGN | STASIUN PONDOK KOPI | Kota Administrasi Jakarta Timur | 0208-D2-PGB-IDM-FTGN-JAKARTA2 | 36.91.125.175 | 36.91.125.174 | 10.66.176.1/27 | 1-70924371025 | 0 | 936481 ¦ Frans Edo | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | idrus | Alfian | [13 empty] | REDHO | aqis
21 | 2026-09-09 | JAKARTA 2 | DANI HIDAYAT | FBGN | KOPKAR INDOMOBIL | Kota Administrasi Jakarta Timur | 0208-D2-JTN-IDM-FBGN-JAKARTA2 | 36.89.139.187 | 36.89.139.186 | 10.66.44.33/27 | 1-70924371382 | 0 | 0 | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | haidar | Alfian | [13 empty] | REDHO | aqis
22 | 2026-09-09 | JAKARTA 2 | DANI HIDAYAT | TJVY | APARTEMEN EAST PARK | Kota Administrasi Jakarta Timur | 0208-D2-PGG-IDM-TJVY-JAKARTA2 | 36.91.177.111 | 36.91.177.110 | 10.66.180.161/27 | 1-73103295886 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | ferdi | Alfian | [13 empty] | REDHO | Rafa
23 | 2026-09-09 | JEMBER | ARIYANTO | TLN2 | TIMOR RAYA KM 9 | Kota Kupang | 0208-D3-OSP-IDM-TLN2-JEMBER | 36.93.241.35 | 36.93.241.34 | 10.76.7.161/27 | 1-71840326131 | 0 | 1600120 ¦ Sahril Dian Hasapi | STARTWORK | ITSC | Pre Config SD-WAN | Lollyta |  |  | Kevin | Alfian | [13 empty] | REDHO | Rafa
24 | 2026-09-09 | JEMBER | ARIYANTO | TWZJ | TIMOR RAYA KM 12 | Kota Kupang | 0208-D3-OSP-IDM-TWZJ-JEMBER | 36.93.241.67 | 36.93.241.66 | 10.76.7.193/27 | 1-71840188069 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | ITSC | Pre Config SD-WAN | Lollyta |  |  | Adnan | Redho | [13 empty] | REDHO | Rafa
25 | 2026-09-09 | LEBAK | DANIEL WARDHANA | T19E | RAYA CILEGON | Kota Cilegon | 0208-D2-CLG-IDM-T19E-LEBAK | 36.67.136.235 | 36.67.136.234 | 10.73.19.160/27 | 1-71838014310 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | hilmi | [14 empty] | REDHO | Rafa
26 | 2026-09-09 | LEBAK | DANIEL WARDHANA | T2AF | RAYA BINUANGEUN WANASALAM | Kabupaten Lebak | 0208-D2-MLP-IDM-T2AF-LEBAK | 36.93.110.81 | 36.93.110.80 | 10.73.54.224/27 | 1-71840754938 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | mando | [14 empty] | REDHO | Rafa
27 | 2026-09-09 | LEBAK | DANIEL WARDHANA | T2YR | TRIP JAMAK SARI | Kota Serang | 0208-D2-CWN-IDM-T2YR-LEBAK | 36.66.124.129 | 36.66.124.128 | 10.73.32.224/27 | 1-71838106366 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | pasha | [14 empty] | REDHO | Rafa
28 | 2026-09-09 | LEBAK | DANIEL WARDHANA | T42Q | SAMANG RAYA | Kota Cilegon | 0208-D2-LKG-IDM-T42Q-LEBAK | 36.66.121.205 | 36.66.121.204 | 10.73.20.64/27 | 1-71838106718 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | raihaan | [14 empty] | REDHO | Rafa
29 | 2026-09-09 | LEBAK | DANIEL WARDHANA | T8SF | RAYA KURANJI SERANG | Kota Serang | 0208-D2-SEG-IDM-T8SF-LEBAK | 36.91.16.59 | 36.91.16.58 | 10.73.40.224/27 | 1-71841517162 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | daris | [14 empty] | REDHO | Rafa
30 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TFM1 | KASERANGAN | Kabupaten Serang | 0208-D2-CRS-IDM-TFM1-LEBAK | 36.94.77.71 | 36.94.77.70 | 10.73.49.192/27 | 1-71838892618 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | rayyan | [14 empty] | REDHO | Rafa
31 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TGWZ | KRANGGOT CILEGON | Kota Cilegon | 0208-D2-CLG-IDM-TGWZ-LEBAK | 36.89.139.201 | 36.89.139.200 | 10.73.21.224/27 | 1-71837369673 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ivansyah | [14 empty] | REDHO | Rafa
32 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TIKX | KITAPA SERANG | Kota Serang | 0208-D2-SEG-IDM-TIKX-LEBAK | 36.94.77.181 | 36.94.77.180 | 10.73.50.160/27 | 1-71839162970 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | idrus | [14 empty] | REDHO | Rafa
33 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TIM4 | SEPANG MOUNTAIN | Kota Serang | 0208-D2-SEG-IDM-TIM4-LEBAK | 36.95.212.97 | 36.95.212.96 | 10.73.42.224/27 | 1-71841517514 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | haidar | [14 empty] | REDHO | Rafa
34 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TLI7 | KAMPUNG NAMBO | Kabupaten Serang | 0208-D2-CWN-IDM-TLI7-LEBAK | 36.66.124.127 | 36.66.124.126 | 10.73.25.160/27 | 1-71840910994 | 0 | 1600120 ¦ Sahril Dian Hasapi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ferdi | [14 empty] | REDHO | Rafa
35 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TQC6 | WANASALAM LEBAK | Kabupaten Lebak | 0208-D2-MLP-IDM-TQC6-LEBAK | 36.92.153.127 | 36.92.153.126 | 10.73.44.64/27 | 1-71840140770 | 0 | 20015070 ¦ Alfian Hafidzh | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Kevin | [14 empty] | REDHO | Rafa
36 | 2026-09-09 | LEBAK | DANIEL WARDHANA | TTBQ | PALM HILLS | Kota Cilegon | 0208-D2-LKG-IDM-TTBQ-LEBAK | 36.66.121.197 | 36.66.121.196 | 10.73.24.32/27 | 1-71839585138 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Adnan | [14 empty] | REDHO | Rafa
37 | 2026-09-09 | PALEMBANG | FAIZUL HAMDI | T9DP | MAYOR ZEN 34 | Kota Palembang | 0208-D1-PGC-IDM-T9DP-PALEMBANG | 36.67.166.231 | 36.67.166.230 | 10.53.48.192/27 | 1-71862560914 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | ITSC | Pre Config SD-WAN | Ayyub |  |  | hilmi | [14 empty] | FRANS | Rafa
38 | 2026-09-09 | PALEMBANG | FAIZUL HAMDI | TK19 | MAYOR ZEN 2 | Kota Palembang | 0208-D1-PGC-IDM-TK19-PALEMBANG | 36.67.174.45 | 36.67.174.44 | 10.53.48.160/27 | 1-71861605014 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | ITSC | Pre Config SD-WAN | Ayyub |  |  | mando | [14 empty] | FRANS | Rafa
39 | 2026-09-09 | PALEMBANG | FAIZUL HAMDI | TOM3 | SRIJAYA NEGARA UNSRI | Kota Palembang | 0208-D1-PGC-IDM-TOM3-PALEMBANG | 36.67.166.117 | 36.67.166.116 | 10.53.41.160/27 | 1-71861033606 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | ITSC | Pre Config SD-WAN | Ayyub |  |  | pasha | [14 empty] | FRANS | Rafa
40 | 2026-09-09 | PALEMBANG | FAIZUL HAMDI | TXB9 | WAY HITAM | Kota Palembang | 0208-D1-BKS-IDM-TXB9-PALEMBANG | 36.91.146.235 | 36.91.146.234 | 10.53.22.96/27 | 1-71859673000 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | ITSC | Pre Config SD-WAN | Ayyub |  |  | raihaan | [14 empty] | FRANS | Rafa
41 | 2026-09-09 | PARUNG | BAGUS RAMANDITA | T29J | SRENGSENG SAWAH 2 | Kota Administrasi Jakarta Selatan | 0208-D2-SMI-IDM-T29J-PARUNG | 36.67.188.185 | 36.67.188.184 | 10.46.87.64/27 | 1-71806313225 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | daris | [14 empty] | FRANS | Rafa
42 | 2026-09-09 | PARUNG | BAGUS RAMANDITA | T6UF | POINT APT EMERALD BINTARO | Kota Tangerang Selatan | 0208-D2-CLD-IDM-T6UF-PARUNG | 36.95.158.211 | 36.95.158.210 | 10.46.15.192/27 | 1-71825152129 | 0 | 0 | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | rayyan | [14 empty] | FRANS | Rafa
43 | 2026-09-09 | PARUNG | BAGUS RAMANDITA | TOKE | POINT APARTEMEN THE BREEZE | Kota Tangerang Selatan | 0208-D2-BIN-IDM-TOKE-PARUNG | 36.94.77.195 | 36.94.77.194 | 10.46.44.0/27 | 1-71824105506 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ivansyah | [14 empty] | FRANS | Rafa
44 | 2026-09-09 | PARUNG | BAGUS RAMANDITA | TZKT | M KAHFI 2 NO 14 | Kota Administrasi Jakarta Selatan | 0208-D2-JAG-IDM-TZKT-PARUNG | 36.89.117.243 | 36.89.117.242 | 10.46.161.0/27 | 1-71824104802 | 0 | 995388 ¦ Ferry Muhammad F | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | idrus | [14 empty] | FRANS | Rafa
45 | 2026-09-09 | PARUNG | BAGUS RAMANDITA | TNGR | SMP 211 | Kota Administrasi Jakarta Selatan | 0208-D2-JAG-IDM-TNGR-PARUNG | 36.88.251.67 | 36.88.251.66 | 10.46.39.32/27 | 1-71803949950 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | haidar | [14 empty] | FRANS | Rafa
46 | 2026-09-09 | PARUNG | BAGUS RAMANDITA | FA93 | OBRIGADO | Kota Tangerang Selatan | 0208-D2-BIN-IDM-FA93-PARUNG | 36.95.158.123 | 36.95.158.122 | 10.46.17.129/27 | 1-70929405575 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ferdi | [14 empty] | FRANS | Rafa
47 | 2026-09-09 | PURWAKARTA | JUNAEDI | T5WS | MUTIARA BEKASI CENTER | Kota Bekasi | 0208-D2-KRA-IDM-T5WS-PURWAKARTA | 36.94.37.229 | 36.94.37.228 | 10.59.31.96/27 | 1-71826815421 | 0 | 855457 ¦ Dwi Syifa | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Kevin | [14 empty] | FRANS | Rafa
48 | 2026-09-09 | PURWAKARTA | JUNAEDI | T96L | TAMAN NAROGONG 4 | Kota Bekasi | 0208-D2-PKY-IDM-T96L-PURWAKARTA | 36.92.212.103 | 36.92.212.102 | 10.59.56.192/27 | 1-71826044182 | 0 | 936573 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Adnan | [14 empty] | FRANS | Rafa
49 | 2026-09-09 | PURWAKARTA | JUNAEDI | T9JB | GARON TIMUR | Kabupaten Bekasi | 0208-D2-CBG-IDM-T9JB-PURWAKARTA | 36.93.110.177 | 36.93.110.176 | 10.59.45.128/27 | 1-71932184859 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | hilmi | [14 empty] | FRANS | Rafa
50 | 2026-09-09 | PURWAKARTA | JUNAEDI | TGMR | SUNCITY SQUARE | Kota Bekasi | 0208-D2-KRA-IDM-TGMR-PURWAKARTA | 36.89.228.75 | 36.89.228.74 | 10.59.10.224/27 | 1-71855161996 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | mando | [14 empty] | FRANS | Rafa
51 | 2026-09-09 | PURWAKARTA | JUNAEDI | TXPZ | APT TAMANSARI ISWARA | Kota Bekasi | 0208-D2-PKY-IDM-TXPZ-PURWAKARTA | 36.95.107.35 | 36.95.107.34 | 10.59.57.160/27 | 1-71833176346 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | pasha | [14 empty] | FRANS | Rafa
52 | 2026-09-09 | TANGERANG 1 | ADE SISWANTO | TG37 | BOJONG | Kabupaten Tangerang | 0208-D2-CKA-IDM-TG37-TANGERANG1 | 36.67.59.209 | 36.67.59.208 | 10.43.52.225/27 | 1-71795772313 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | raihaan | [14 empty] | FRANS | Rafa
53 | 2026-09-09 | TANGERANG 1 | ADE SISWANTO | TK26 | JAHA BALARAJA | Kabupaten Tangerang | 0208-D2-BLJ-IDM-TK26-TANGERANG1 | 36.91.62.33 | 36.91.62.32 | 10.43.42.1/27 | 1-71798607947 | 0 | 20015127 ¦ Alfian Hafidzh | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | daris | [14 empty] | FRANS | Rafa
54 | 2026-09-09 | TANGERANG 1 | ADE SISWANTO | TNBJ | OLEK BALARAJA | Kabupaten Tangerang | 0208-D2-BLJ-IDM-TNBJ-TANGERANG1 | 36.95.207.69 | 36.95.207.68 | 10.43.28.129/27 | 1-71804031268 | 0 | 855457 ¦ Dwi Syifa | STARTWORK | ITSC | Pre Config SD-WAN | Isnu |  |  | rayyan
55 | 2026-09-09 | TANGERANG 1 | ADE SISWANTO | FWJJ | GEBANG | Kabupaten Tangerang | 0208-D2-PSK-IDM-FWJJ-TANGERANG1 | 36.95.189.209 | 36.95.189.208 | 10.43.47.32/27 | 1-71803586165 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ivansyah
56 | 2026-09-09 | TANGERANG 1 | ADE SISWANTO | T9DC | RAYA SERANG KM 16 | Kabupaten Tangerang | 0208-D2-CKA-IDM-T9DC-TANGERANG1 | 36.95.107.31 | 36.95.107.30 | 10.43.56.192/27 | 1-71803767236 | 0 | 936481 ¦ Frans Edo | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | idrus
57 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | T1NY | ANGGREK CAKRA 25 | Kota Administrasi Jakarta Barat | 0208-D2-PLM-IDM-T1NY-TANGERANG2 | 36.92.161.29 | 36.92.161.28 | 10.58.27.64/27 | 1-71811955640 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | haidar
58 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | T66O | PERGUDANGAN SENTRA KOSAMBI | Kabupaten Tangerang | 0208-D2-TGA-IDM-T66O-TANGERANG2 | 36.92.134.105 | 36.92.134.104 | 10.58.10.192/27 | 1-71812184344 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | ferdi
59 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | TC5E | SWADARMA 2 | Kota Administrasi Jakarta Selatan | 0208-D2-KAL-IDM-TC5E-TANGERANG2 | 36.67.136.133 | 36.67.136.132 | 10.58.146.64/27 | 1-71812476752 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Kevin
60 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | TMKN | MERUYA SELATAN | Kota Administrasi Jakarta Barat | 0208-D2-SLP-IDM-TMKN-TANGERANG2 | 36.67.177.65 | 36.67.177.64 | 10.58.139.160/27 | 1-71813249808 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | Adnan
61 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | TNQM | MUCHTAR RAYA 2 | Kota Administrasi Jakarta Selatan | 0208-D2-KAL-IDM-TNQM-TANGERANG2 | 36.67.190.251 | 36.67.190.250 | 10.58.135.128/27 | 1-71812183992 | 0 | 20005211 ¦ M. Redho Ali Said | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | hilmi
62 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | TR58 | PERANCIS DADAP | Kabupaten Tangerang | 0208-D2-TGA-IDM-TR58-TANGERANG2 | 36.89.128.131 | 36.89.128.130 | 10.58.108.224/27 | 1-71811264120 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | mando
63 | 2026-09-09 | TANGERANG 2 | DENI YULIUS | T8XA | JALAN E | Kota Administrasi Jakarta Barat | 0208-D2-PLM-IDM-T8XA-TANGERANG2 | 36.92.120.7 | 36.92.120.6 | 10.58.48.161/27 | 1-71836545888 | 0 | 20015074 ¦ Alfian Hafidzh | STARTWORK | HGT | Pre Config SD-WAN | Rian |  |  | pasha
64 | 2026-09-09 | PALOPO | 0 | TLAG | PUE BONGO NO 59 | Kota Palu | 0208-D5-PLA-IDM-TLAG-PALOPO | 36.64.167.225 | 36.64.167.224 | 10.75.33.0/27 | 1-71826910873 | 0 | 1600120 ¦ Sahril Dian Hasapi | STARTWORK | ITSC | Pre Config SD-WAN | Deni |  |  | raihaan | [15 empty] | Rafa
65 | 2026-09-09 | PALOPO | 0 | TAZ7 | DAYODARA NO 15 | Kota Palu | 0208-D5-PLA-IDM-TAZ7-PALOPO | 36.95.55.209 | 36.95.55.208 | 10.75.33.161/27 | 1-71832579169 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | ITSC | Pre Config SD-WAN | Deni |  |  | daris | [15 empty] | Rafa
66 | 2026-09-09 | PALOPO | 0 | TNQR | TANJUNG SANTIGI | Kota Palu | 0208-D5-PLB-IDM-TNQR-PALOPO | 36.92.208.189 | 36.92.208.188 | 10.75.34.33/27 | 1-71833054240 | 0 | 985483 ¦ Kevin Dwi | STARTWORK | ITSC | Pre Config SD-WAN | Deni |  |  | rayyan | [15 empty] | Rafa
67 | 2026-09-09 | DC JAKARTA 2 | #N/A | T4JI | SELAT PATINTI F 1 | Kota Administrasi Jakarta Timur | 0208-D2-KLD-IDM-T4JI-DCJAKARTA2 | 36.92.143.123 | 36.92.143.122 | 10.66.15.32/27 | 1-73104693023 | 0 | 0 | STARTWORK | ITSC | Review Order TSQ SDWAN | Isnu |  |  | ivansyah | [15 empty] | Rafa
68 | [35 empty] | Rafa
69 | [35 empty] | Rafa
70 | [35 empty] | Rafa
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Mas @Agung Maulana terlampir Plan aktivasi untuk hari ini Kamis, tanggal 03 Sep 2026

## Lembar1
Activation Status | OGP
Branch Name | Site Code
BANJARMASIN | FT9C
TDDA
BEKASI | T1WK
TCKX
JAKARTA 1 | TNG9
JAKARTA 2 | TADX
TCBD
LEBAK | TFT1
TLM1
TPRH
TQBE
PARUNG | TANU
TTYU
PURWAKARTA | TABD
TKB9
TANGERANG 2 | T0FI
TVWE
TXVF
Grand Total